## Slide 1
Tasks | Feb | Mar | Apr | May
 | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | M | J | J | A | S | O | N | D
Literature Review & Training Session |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
An automatic data acquisition demo |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
A well-documented SyntheX repo |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Integrate all packages into a sole package |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Construct a data exchange channel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Design an automatic pipeline for data acquisition, training, and 2D/3D registration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Simulate the scene of projective visualization in unity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Validate the program on phantom and write a report about the validation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Design a software with user-friendly GUI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Improve robustness and have a debug log |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Validate the program on cadaveric and write a report about the validation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Mixed Reality Visualization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Feb 6 - Feb 9
Feb 8 - Feb 21
Feb 1 - Mar 6
Mar 13 – Mar 27
Mar 1 – Mar 23
Apr 1 – Apr 15
Apr 13 – Apr 17
Apr 18 – Apr 25
Mar 31 – Apr 4
Mar 20 – Mar 27
Apr 25 – May 15
Mar 27 – Mar 30

## Slide 2: Slide Title
Task bars (length = duration)
Milestones
To change the length of the duration bars go to Format/Size (on far right). For extreme length changes, ungroup the duration bars and scale the highlight independently.